## Project Plan
Module | Activities | Assigned To | Estimated Completion | Comments
Invoice Generation | BVR data sync from KRONOS | Abhishek Bansal | 2021-09-13
| PPE, PF, ESI, Bonus Calculation | Abhishek Bansal | 2021-09-14
| Backend API Creation | Abhishek Bansal | 2021-09-14
| Manual option upload for non CWFM plants API | Abhishek Bansal | 2021-09-15
| Manual option upload for non CWFM plants UI | Tanveer Alam | 2021-09-15
| BVR UI development | Tanveer Alam | 2021-09-14 |  | Abhishek Bansal
| Invoice generation on screen for BSR/Service separately | Tanveer Alam | 2021-09-15 |  | Bhakti Thombre
| PDF generation | Tanveer Alam | 2021-09-15 |  | Divya Gupta
| Email Functionality | Praveen Badiger | 2021-09-20 |  | Praveen Badiger
Tanveer Alam
Dipute Management | Backend API Creation | Abhishek Bansal | 2021-09-22
| Dispute workflow screen | Tanveer Alam | 2021-09-23
| UI development (Tracking, Listing, Assignment) | Tanveer Alam | 2021-09-23
| Email Functionality | Praveen Badiger | 2021-09-23
Bill Approval Workflow | Backend API Creation | Divya Gupta | 2021-09-22
| Email functionality based on Bill amount and Position | Divya Gupta | 2021-09-23
| Bill Status Workflow UI screen | Bhakti Thombre | 2021-09-23
Contractor Digital Signature | Backend API Creation | Divya Gupta | 2021-09-16
| Temp PDF generation based on the final approved bill | Tanveer Alam | 2021-09-16
| Storing the Signed bill on Azure Storage, DB and sending it to contractor and concerned parties. | Divya Gupta | 2021-09-17
| UI Development | Tanveer Alam | 2021-09-17
| Email Functionality | Praveen Badiger | 2021-09-23
Service Entry Posting | Service Entry Creation RFC integration | Praveen Badiger | 2021-09-16
| Service Entry status monitoring API | Praveen Badiger | 2021-09-17
| Service Entry status monitoring UI | Bhakti Thombre | 2021-09-18
| Email Functionality | Praveen Badiger | 2021-09-23
MIRO Posting | SAP RFC integration for the Service Entry | Praveen Badiger | 2021-09-22
| MIRO Posting status monitoring API | Praveen Badiger | 2021-09-23
| MIRO Posting status monitoring UI | Bhakti Thombre | 2021-09-23
| Email Functionality | Praveen Badiger | 2021-09-23
Final Bill posting to UKSC | RFC integration with SAP for fetching the Case Manager ID API | Praveen Badiger | 2021-09-22
| Case Manager status monitoring UI | Tanveer Alam | 2021-09-23
| Email Functionality | Praveen Badiger | 2021-09-23
Admin | Transaction Data | Praveen Badiger | 2021-09-23
| Master Management | Praveen Badiger | 2021-09-23
| UI Development | Bhakti Thombre | 2021-09-24
Reports and Dashboard | BVR Reports API | Abhishek, Divya, Praveen | 2021-09-27
| BVR Reports UI | Tanveer, Bhakti | 2021-09-27
Formulas:
Estimated Completion = SUM([Estimated Completion, row above],1)