## MgmtOverview
Project Name | CWFM Bill Generation
Milestone | Start Date | End Date | Revised Target | Status | Remarks/Comments
Preparation & InfraSetup | 2021-07-05 | 2021-07-21 |  | Completed
Requirement Gathering | 2021-07-05 | 2021-07-23 | 2021-08-22 | In-Progres | RG Completed documentation in progress, Shall be circulated for by next week for signoff.
Solution Design | 2021-07-13 | 2021-07-25 | 2021-08-24 | In-Progres | DB Design completed (80%), Solution design completed 60%
Development | 2021-08-02 | 2021-08-29 | 2021-09-28 | In-Progres | Application framework design completed, Backend development in progress - Admin modules expected to be completed by 25-Aug-21
Testing | 2021-08-09 | 2021-09-04 | 2021-09-29 | Planned
UAT | 2021-08-21 | 2021-09-04 | 2021-09-29 | Planned
Go Live | 2021-09-07 | 2021-09-11 | 2021-09-30 | Planned
Legends
In-Progress
Delayed
Completed
Severally Delayed
Formulas:
Revised Target = [End Date]+30

## Detailed
Project Name |  | INDS000214 / CWFM - Bill Generation
Milestone | # | Task/Activity | Dependency | Start Date | Effort Days | End Date | Actual date | Responsibility | Status | Owner | Remarks/Comments
Preparation |  |  |  | 2021-07-05 | 25 | 2021-07-20
| 1 | Project Plan Estimated Milestones | N/A | 2021-07-05 | 3 | 2021-07-08 |  | Blazeclan | WIP | Kashish Ambwani
| 2 | Document Repository Creation | N/A | 2021-07-06 | 1 | 2021-07-07 |  | Blazeclan/UTCL | Completed | Ashwin Taware/Vijay Singh | Access to share-point given by Vijay
| 3 | Solution Design Document/Functional Requirement Specification | N/A | 2021-07-12 | 5 | 2021-07-17 |  | Blazeclan | WIP | Kashish Ambwani | Delay on Kashish
| 4 | Approval for Solution Design Document/Business Blueprint | Task# 3 | 2021-07-19 | 1 | 2021-07-20 |  | UTCL | Yet to Start | UTCL Module Leads
| 5 | SOW Creation | N/A | 2021-07-05 | 4 | 2021-07-09 |  | Blazeclan | WIP | Subhasish Baruah
| 6 | Approval of SOW | Task# 5 | 2021-07-12 | 1 | 2021-07-13 |  | UTCL | Pending | Vijay Singh
| 7 | Technical Specification Document Creation | Task# 4 | 2021-07-12 | 5 | 2021-07-17 |  | Blazeclan | WIP | Abhishek Bansal | Delay on Abhishek
| 8 | Approval of Technical Specification Document | Task# 7 | 2021-07-19 | 1 | 2021-07-20 |  | UTCL | Pending | Vijay Singh
| 9 | BOM Preparation | Task# 7 | 2021-07-12 | 3 | 2021-07-15 |  | Blazeclan | WIP | Abhishek Bansal | Approved for Dev.
| 10 | BOM Approval | Task# 9 | 2021-07-15 | 1 | 2021-07-16 |  | UTCL | WIP | Vijay Singh / BRM | Approved for Dev.
Infrastructure/DevOps Setup |  |  |  | 2021-07-12 | 19 | 2021-07-21
| 1 | Azure Resource Group Creation Access | N/A | 2021-07-12 | 2 | 2021-07-14 |  | UTCL | Completed | Krishna Tiwari / UTCL | Delayed by 3-4 days.(Recoverable)
| 2 | Creation of Dev/QA environments | Task# 1 | 2021-07-12 | 3 | 2021-07-15 |  | Blazeclan | Delayed | Abhishek Bansal | Technology Stack = .Net 5.0, Angular and MS SQL DB
| 3 | End Point URL Creation/IP and DNS Configuration | Task# 2 | 2021-07-12 | 3 | 2021-07-15 |  | UTCL | Pending | Cloud Team | QA Demo should be given first
| 4 | Procurement of SSL Certificate(If needed) | N/A |  |  |  |  | UTCL | Yet to Start | VIjay Singh | SSL should be done on Load Balancer
| 5 | DevOps(CI/CD) Pipeline | Task# 2 | 2021-07-12 | 5 | 2021-07-17 |  | Blazeclan | Delayed | Abhishek Bansal | Delay on Abhishek
| 6 | Common Frameworks | Task# 2 | 2021-07-12 | 2 | 2021-07-14 |  | Blazeclan | WIP | Abhishek Bansal
| 7 | Database Setup/Config | Task# 2 | 2021-07-12 | 2 | 2021-07-14 |  | Blazeclan | Completed | Abhishek Bansal | Dependent on BOM and TSD
| 8 | Azure WAF Clearance(Firewall) | Task# 3 | 2021-07-19 | 2 | 2021-07-21 |  | UTCL/Blazeclan | Delayed | UTCL Cloud Team, Kashish Ambwani | Delay on Abhishek
Requirement Gathering |  |  |  | 2021-07-05 | 73 | 2021-07-23
| 1 | Functional Requirement Gathering | N/A | 2021-07-05 | 11 | 2021-07-16 |  | Blazeclan | Delayed | Kashish Ambwani | Functional Requirmenet Specification Document provided to Vijay. Review Pending
| 2 | Analysis of Requirement | Task# 1 | 2021-07-12 | 3 | 2021-07-15 |  | Blazeclan | WIP | Kashish Ambwani
| 3 | Technical Specification Documents - SAP and UKSC Integration | Task# 1 | 2021-07-08 | 15 | 2021-07-23 |  | UTCL/Blazeclan | WIP | SAP Team, Abhishek Bansal
| 4 | Understanding the Stakeholder needs | N/A | 2021-07-05 | 5 | 2021-07-10 |  | Blazeclan | WIP | Kashish Ambwani | Delayed by 3-4 days.(Recoverable)
| 5 | Define the System | Task# 1,3 | 2021-07-05 | 5 | 2021-07-10 |  | Blazeclan | WIP | Kashish Ambwani | Delayed by 3-4 days.(Recoverable)
| 6 | Manage Scope of System | Task# 5 | 2021-07-05 | 5 | 2021-07-10 |  | Blazeclan | WIP | Kashish Ambwani | Delayed by 3-4 days.(Recoverable)
| 7 | Refine System Definition | Task# 5,6 | 2021-07-05 | 5 | 2021-07-10 |  | Blazeclan | WIP | Kashish Ambwani | Delayed by 3-4 days.(Recoverable)
| 8 | Categorization of Similar Requirements | Task# 5 | 2021-07-05 | 5 | 2021-07-10 |  | Blazeclan | WIP | Kashish Ambwani | Delayed by 3-4 days.(Recoverable)
| 9 | Dependecies between Requirements | Task# 1,2,3 | 2021-07-05 | 5 | 2021-07-10 |  | Blazeclan | WIP | Kashish Ambwani | Delayed by 3-4 days.(Recoverable)
| 10 | Capturing process for testing, validation and Quality Control | Task# 1,2,5,6 | 2021-07-05 | 5 | 2021-07-10 |  | Blazeclan | WIP | Kashish Ambwani | Delayed by 3-4 days.(Recoverable)
| 11 | Creation of Requirement Traceability Matrix | Task# 1 | 2021-07-14 | 3 | 2021-07-17 |  | Blazeclan | WIP | Kashish Ambwani
| 12 | Functional Requirement Specification | Task# 1 | 2021-07-12 | 5 | 2021-07-17 |  | Blazeclan | Completed | Kashish Ambwani
| 13 | Approval for Functional Requirement | Task# 12 | 2021-07-19 | 1 | 2021-07-20 |  | UTCL | Pending | Module Leads
Solution Design |  |  |  | 2021-07-13 | 25 | 2021-07-25
| 1 | Design for Database | N/A | 2021-07-13 | 3 | 2021-07-16 |  | Blazeclan | Delayed | Abhishek Bansal | Inclusive of Master Data Design
| 2 | ER Diagram/DB Mapping | Task# 1 | 2021-07-13 | 3 | 2021-07-16 |  | Blazeclan | Delayed | Abhishek Bansal
| 3 | Design for Wireframes | N/A | 2021-07-14 | 4 | 2021-07-18 |  | Blazeclan | Delayed | Kashish Ambwani
| 4 | Approval for Wireframes | Task# 3 | 2021-07-19 | 1 | 2021-07-20 |  | UTCL | Pending | HO HR / Technical Team
| 5 | Approval for Design of Database and Interface | Task# 1,2 | 2021-07-19 | 1 | 2021-07-20 |  | UTCL | Pending | Vijay Singh
| 6 | Integration Approach Document | Task# 4,5 | 2021-07-19 | 5 | 2021-07-24 |  | Blazeclan | Yet to Start | Abhishek Bansal
| 7 | User Story Creation | N/A | 2021-07-20 | 2 | 2021-07-22 |  | Blazeclan | Delayed | Kashish Ambwani | Dependent on FRS
| 8 | Scrum Board Creation | Task# 7 | 2021-07-21 | 2 | 2021-07-23 |  | Blazeclan | Delayed | Kashish Ambwani
| 9 | Providing access to Backend Systems/APIs | N/A | 2021-07-21 | 4 | 2021-07-25 |  | UTCL | Pending | Gaurang Karasaliya / SAP Team / Vijay Singh | API Documentation Required
Development |  |  |  | 2021-08-02 | 60 | 2021-08-29
| 1 | Develop System Modules | Dependent on Solution Design | 2021-08-02 | 20 | 2021-08-22 |  | Blazeclan | WIP | Abhishek Bansal
| 2 | Integrate System Modules | Task# 1 | 2021-08-09 | 5 | 2021-08-14 |  | Blazeclan | Yet to Start | Abhishek Bansal
| 3 | RFC Development and Testing | Dependent on SAP,UKSC | 2021-08-09 | 15 | 2021-08-24 |  | UTCL | Yet to Start | Pradeep Yadavalli & Vishal
| 4 | UKSC Development and Testing | Dependent on SAP,UKSC | 2021-08-09 | 15 | 2021-08-24 |  | Blazeclan | Yet to Start | Gaurang Karasaliya
| 5 | Unit Testing | Task# 2 | 2021-08-24 | 5 | 2021-08-29 |  | Blazeclan | Yet to Start | Abhishek Bansal
Testing |  |  |  | 2021-08-09 | 35 | 2021-09-04
| 1 | System Testing | Dependent on development | 2021-08-09 | 15 | 2021-08-24 |  | Blazeclan | Yet to Start | Snehal Dashapute
| 2 | Documentation of Issues found during Testing | Task# 1 | 2021-08-10 | 15 | 2021-08-25 |  | Blazeclan | Yet to Start | Snehal Dashapute
| 3 | Iteration Cycle - 1 | Task# 1 | 2021-08-24 | 5 | 2021-08-29 |  | Blazeclan | Yet to Start | Snehal Dashapute
| 4 | Iteration Cycle - 2 | Task# 3 | 2021-08-30 | 5 | 2021-09-04 |  | Blazeclan | Yet to Start | Snehal Dashapute
UAT |  |  |  | 2021-08-21 | 17 | 2021-09-04
| 1 | UAT Test Cases Creation | Requirement traceability Matrix and Test Cases | 2021-08-21 | 3 | 2021-08-24 |  | Blazeclan | Yet to Start | Snehal Dashapute
| 2 | Training Manuals Creation | FRS | 2021-08-21 | 3 | 2021-08-24 |  | Blazeclan | Yet to Start | Kashish Ambwani
| 3 | User Training - Power Users and Departments | Task# 2 | 2021-08-24 | 3 | 2021-08-27 |  | Blazeclan | Yet to Start | Kashish Ambwani
| 4 | UAT Testing | Task# 2,3 | 2021-08-27 | 4 | 2021-08-31 |  | UTCL | Yet to Start | Power users
| 5 | Iteration of Bug Fixes for UAT | Task# 4 | 2021-09-01 | 1 | 2021-09-02 |  | UTCL | Yet to Start | Power users
| 6 | Resolution of Bug Fixes for UAT | Task# 5 | 2021-09-02 | 1 | 2021-09-03 |  | Blazeclan | Yet to Start | Abhishek Bansal
| 7 | UAT Signoff | Task# 6 | 2021-09-02 | 2 | 2021-09-04 |  | UTCL | Yet to Start | UTCL Module Leads
Go Live |  |  |  | 2021-09-07 | 7 | 2021-09-11
| 1 | Deployment Plan | N/A | 2021-09-07 | 2 | 2021-09-09 |  | Blazeclan | Yet to Start | Abhishek Bansal
| 2 | Deployment Plan Approval | Task# 1 | 2021-09-09 | 1 | 2021-09-10 |  | UTCL | Yet to Start | Vijay Singh
| 3 | Release Plan | N/A | 2021-09-07 | 2 | 2021-09-09 |  | Blazeclan | Yet to Start | Kashish Ambwani
| 4 | Release Plan Approval | Task# 3 | 2021-09-09 | 1 | 2021-09-10 |  | UTCL | Yet to Start | Vijay Singh
| 5 | Roll Out | Task# 2,4 | 2021-09-10 | 1 | 2021-09-11 |  | Blazeclan | Yet to Start | Abhishek Bansal, Kashish Ambwani
Project Closure |  |  |  | 2021-09-14 | 7 | 2021-09-18
| 1 | Lessons Learnt | N/A | 2021-09-14 | 1 | 2021-09-15 |  | Blazeclan | Yet to Start | TBD
| 2 | Project Closure Document | N/A | 2021-09-14 | 3 | 2021-09-17 |  | Blazeclan | Yet to Start | TBD
| 3 | Documents Handover | N/A | 2021-09-14 | 3 | 2021-09-17 |  | Blazeclan | Yet to Start | TBD
| 4 | Project Sign-Off | Task# 2,3 | 2021-09-17 | 1 | 2021-09-18 |  | UTCL | Yet to Start | Vijay Singh
Formulas:
End Date = SUM([Start Date]+[Effort Days])

## Contacts
# | Name | Phone No | Email Id | Role | WSR TO
1 | Kashish Ambwani | 8552851419 | kashish.ambwani@blazeclan.com | BA
2 | Sandip Bhole | 8888877048 | sandip.bhole@blazeclan.com | Solution Architect
3 | Sachin Verma | 9041791643 | sachin.verma@blazeclan.com | Guiding Solution Architect
4 | Snehal Dashaspute | 9405835344 | snehal.dashapute@blazeclan.com | Tester / QA
5 | Tanveer Alam | 9860680167 | tanveer.alam@blazeclan.com | Developpers
6 | Bhakti Thombare | 9960788535 | bhakti.thombare@blazeclan.com | Developpers
7 | Abhishek Bansal | 9513112526 | abhishek.bansal@blazeclan.com | Tech Lead
8 | Ashwin Taware | 9987229119 | ashwin.taware@blazeclan.com | PM
9 | Chetan Rathore | 9001810610 / 9001810610 | chetan.rathore@adityabirla.com | UKSC SPOC 1 | Y
10 | Pankaj Kumar Jain | 9887484514 / 8890126000 | pankaj.k.jain@adityabirla.com | UKSC SPOC 2 | Y
11 | Sanjeev MK | 9702098032 | sanjeev.mk@adityabirla.com | SAP MM - Module lead | Y
12 | Vishal A | 9511115476 | vishal.a-v@adityabirla.com | SAP MM - Consultant | Y
13 | Kailash Maheshwari | 9887482087 | kailash.maheshwari@adityabirla.com | SAP FI - Module Lead | Y
14 | Pradeep Yadavalli | 8108000714 | pradeep.yadavalli@adityabirla.com | SAP FI - Consultant | Y
15 | Vijay Kumar Singh | 9769921080 | vijaykumar.singh@adityabirla.com | PM / Tech Lead - Application | Y
16 | Sachin P Channe | 9422136464 | sachin.channe@adityabirla.com | Project Coordinator IT | Y
17 | George Allu | 9885588666 | george.allu@adityabirla.com | HR/ER HO Lead | Y
18 | Annapurani Sankarakrishnan | 9004744753 | annapurani.s@adityabirla.com | HR/ER HO | Y
19 | Gaurang Karasaliya | 9891012015 | gs.karasaliya@adityabirla.com | UKSC - Technical | Y
20 | Raj Khetan | 7089906670 | raj.khetan@adityabirla.com | SPOC Vikram | Y
21 | Ramana Bhogi | 7680993711 | ramana.bhogi@adityabirla.com | SPOC APCW | Y
22 | Jitendra Tanwar | 9285002010 / 8440045454 | jitendra.tanwar@adityabirla.com | SPOC Hirmi | Y
23 | Dhananjayan M G | 8124086932 | dhananjayan.mg@adityabirla.com | SPOC Reddy palyam | Y
24 | Anand Pathak | 9093200243 | anand.pathak@adityabirla.com | SPOC Awarpur | Y
25 | Piryadasrshini Anand |  | priyadarshini.anand@adityabirla.com | HO HR - Manufacturing | N
26 | Martin Mohanty |  | martin.mohanty@adityabirla.com |  | N
27 | Rajan Pillai |  | rajan.pillai@adityabirla.com |  | N
28 | Manoj Tarade |  | manoj.tarade@adityabirla.com | SAP Head | N
29 | Sunil Kothari |  | sunil.kothari@adityabirla.com |  | N
30 | Sombrata Chakrabarti |  | som.chakrabarti@adityabirla.com |  | N
31 | Chandra Sahoo |  | chandra.s.sahu@adityabirla.com | UKSC Head | N

## Power User
Plant | Name | Position | Department | Mobile No | Email | Reporting Manager Email | WSR To
Vikram Cement Works (VC01) | Praveen Jain | SH ER | ER | 9887480318 | praveen.jain@adityabirla.com |  | Y
| Arvind Gupta | PF ER | ER | 9669828046 | arvind.gupta@adityabirla.com | Praveen Jain | Y
Andhara Pradesh Cement Works (AP01) | Ramana Bhogi | SPOC-APCW | ER |  | ramana.bhogi@adityabirlacom |  | Y
| Vijay Vasireddy | Power User | ER | 7036397733 | vijay.vasireddy@adityabirla.com |  | Y
| K P Rao | Finance rep | Accounts |  | kp.rao@adityabirla.com |  | Y
| Sedhuram B | User dept | Mech-1 |  | sedhuram.b@adityabirla.com |  | Y
Hirmi Cement Works | Nidhish Gaur | PF ER | ER | 9759216100 | nidhish.gaur@adityabirla.com |  | Y
BAGHERI CEMENT WORKS | Pankaj Kumar Sharma |  |  | 8290615465 | Pankaj.c.sharma@adityabirla.com